## Instructions
Double Edged product render shot-list example
Purpose | Turn launch needs into a governed render list before production begins.
How to use | Keep the sample rows that fit your launch, remove the rest, add exact variant names, assign an owner, and approve each acceptance check before export.
Status values | Planned, Ready for review, Approved, or Revise. Use the dropdown in the Shot List sheet.
Acceptance rule | A shot is complete only when the named owner can verify the listed visual condition. Approval should not depend on a vague impression such as 'looks good.'
Variants | Replace sample scopes with the exact SKU, colour, finish, packaging, and market combinations that must be delivered.
Platform note | This is a planning example, not a universal marketplace specification. Verify each destination's current image rules before final export.
Companion article | A Product Render Shot List for a Complete Digital Launch
Prepared | 2026-08-30

## Shot List
Section | Shot ID | Purpose | Framing | Variant scope | Acceptance check | Owner | Status | Notes
PDP foundation | PDP-01 | White-background three-quarter hero | Front three-quarter; product centered with crop room | All primary storefront variants | Edges are clean, silhouette is legible, and the product remains consistent across variants | E-commerce | Planned | Lead image for product-detail pages
PDP foundation | PDP-02 | Straight-on pack shape | Front elevation; camera square to the product | Core product family | Proportions, openings, controls, and visible seams match the approved source | Product | Planned | Useful for comparison and catalog grids
PDP foundation | PDP-03 | Rear or underside information view | Rear, base, or underside chosen by information priority | Models with relevant ports, labels, or assembly details | Required information is readable at the intended delivery size and no key feature is hidden | Product | Planned | Use only where the view answers a buyer question
PDP foundation | PDP-04 | Macro material detail | Tight crop on the primary finish | Each distinct material or finish family | Roughness, grain, coating, and edge treatment read clearly without false gloss or texture scale | Brand | Planned | Choose the material that carries the product's value
PDP foundation | PDP-05 | Macro feature detail | Close view aligned to the feature's use | Feature-bearing variants | The mechanism or interface is visible and the frame explains what the feature does | Product | Planned | Do not repeat PDP-04 unless the feature and material are the same decision
PDP foundation | PDP-06 | Variant comparison grid | Matched camera and crop across tiles | Approved colours, finishes, and configurations | Only approved differences change; camera, lighting, scale, and product pose remain controlled | E-commerce | Planned | Use exact storefront variant names
PDP foundation | PDP-07 | Scale cue | Product shown with an unambiguous, honest size reference | One representative variant unless size changes | The cue helps the buyer judge physical size without implying a use or compatibility the product does not support | Product | Planned | A dimension graphic can replace lifestyle context when clearer
PDP foundation | PDP-08 | Packaging view | Closed package plus product or package-only view | Packaging variants that affect delivery expectation | Pack count, included parts, and exterior appearance match what the customer receives | Operations | Planned | Optional when packaging does not help the purchase decision
Story and launch | STY-01 | Controlled studio hero | Front three-quarter with deliberate negative space | Primary campaign variant | The product remains the dominant subject and the composition leaves usable room for campaign copy | Brand | Planned | Campaign anchor distinct from the white-background PDP hero
Story and launch | STY-02 | Studio profile | Side profile or silhouette-led view | Primary silhouette family | The outline is immediately recognizable and no perspective distortion misrepresents proportions | Brand | Planned | Useful for editorial layouts and product-family rhythm
Story and launch | STY-03 | Elevated material detail | Premium close crop with controlled light falloff | Hero finish | The frame shows why the material matters while preserving accurate colour and texture | Brand | Planned | Avoid decorative detail with no buyer value
Story and launch | CTX-01 | Primary lifestyle scene | Product in its most important use context | Primary campaign variant | Scale, contact, shadows, and environmental reflections feel physically coherent and the use case is credible | Marketing | Planned | Choose the context that carries the main launch story
Story and launch | CTX-02 | Alternate lifestyle scene | Different setting or daypart with the product still dominant | Secondary campaign need | The alternate scene adds a distinct message or audience rather than repeating CTX-01 with new decoration | Marketing | Planned | Remove if it does not earn a separate placement
Story and launch | FT-01 | Primary feature diagram | Clear product view with one focused annotation system | Feature-bearing variants | The diagram explains one mechanism or benefit without tiny labels, dense icon clouds, or unsupported performance claims | Product | Planned | Keep detailed text in accessible HTML or page copy
Story and launch | FT-02 | Secondary feature diagram | Different view selected for the second system | Feature-bearing variants | The visual answers a separate buyer question and does not duplicate FT-01 | Product | Planned | Delete the row when there is no second useful feature
Story and launch | MKT-01 | Flexible derivative crop | Composition designed to survive square, portrait, and wide crops | Primary campaign variant | The product stays legible in every required crop and no crop removes a necessary feature | Marketing | Planned | Record exact channel dimensions in Notes before production
Note on A1: PDP foundation covers durable catalog needs. Story and launch covers campaign, context, feature, and derivative shots.
Note on E1: Replace sample wording with exact SKU, colour, finish, packaging, and market combinations.
Note on F1: Write a visible, reviewable condition. Avoid subjective checks such as 'looks premium.'
Note on H1: Use the dropdown. Only the assigned owner should mark a shot Approved.